## High Level Process
We hope you find this sample implementation plan helpful. If you have any questions or are looking for a modern legal operations software to track and manage your legal expenses, please reach out to us!
| www.simplelegal.com | info@simplelegal.com

## Timeline
[10 empty] | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6
|  | Company Name |  |  |  | -> Change Start Date | time axis 2018-03-29 to 2018-08-25
Title Row | Optional | Task | Assigned | Status | Start Date | Target Date | % Done | +/- | Notes
T |  | Setup |  |  |  |  | 21.43%
|  | Customer provides sample matter list or initial workbook matter data | Customer | Complete | 2018-04-03 | 2018-04-17 | 100%
|  | Update workbook /requirements for client to fill out | e-Billing | Not Started | 2018-04-11 | 2018-04-13 | 50% | 15 | Customize workbook based on matter data received and CTB
|  | Welcome Call | Customer / e-Billing | Not Started | 2018-04-16 | 2018-04-16 | 0% | 18 | A introductory call where the CSM will learn more about your legal team structure. Confirm project scope. Review high level project steps and provide guidelines for requirements/legal data needed.
|  | Complete Initial Workbook / Requirements | Customer | Not Started | 2018-04-16 | 2018-04-21 | 0% | 23 | Customer to fill out what they know already. It is ok if the customer does not know all of the requirements yet your CSM will work with you to do this during the requirements phase.
|  | Confirm additional team members and upcoming meeting schedule | Customer / e-Billing | Not Started |  |  | 0%
|  | Build Draft Custom Implementation Plan | e-Billing | Not Started |  |  | 0% |  | Your CSM will build a custom implementation plan
|  | Project Kick Off/ Implementation Review Call | Customer / e-Billing | Not Started |  |  | 0% |  | Review and sign off on implementation plan and timeline
T |  | e-Billing Requirements |  |  |  |  | 0%
|  | User info and permissions | Customer | Not Started |  |  | 0%
|  | Vendors requirements | Customer | Not Started |  |  | 0%
|  | Business requirements (legal, finance, approval, audit, tax, etc.,) | Customer | Not Started |  |  | 0%
|  | Custom Data | Customer | Not Started |  |  | 0%
| O | Reporting goals | Customer | Not Started |  |  | 0% |  | If reporting requirements cannot be met by standard and adhoc reporting then custom reporting may be required.
|  | Invoice outbound process | Customer | Not Started |  |  | 0%
T |  | System Setup & Data Migration |  |  |  |  | 0%
|  | Set up environment | e-Billing | Not Started |  |  | 0%
|  | Customize/configure e-billing solution | e-Billing | Not Started |  |  | 0% |  | We'll add the custom fields to match the fields you want to import
|  | Import legal operations data | e-Billing | Not Started |  |  | 0% |  | When we're ready, we'll import the full legal data into e-Billing
|  | Test and review for data matching | e-Billing | Not Started |  |  | 0% |  | We'll conduct some final tests and ensure the data matches what we loaded
|  | Custom Data Loaded | e-Billing | Not Started |  |  | 0%
|  | Users Loaded | e-Billing | Not Started |  |  | 0%
|  | Vendors Loaded | e-Billing | Not Started |  |  | 0%
|  | Sign off on data load | e-Billing | Not Started |  |  | 0%
|  | All data loaded | e-Billing | Not Started |  |  | 0% |  | Confirm all data are loaded
T |  | Vendor Setup |  |  |  |  | 0%
|  | Customize vendor onboarding messaging | e-Billing | Not Started |  |  | 0% |  | We'll customize the messaging to reflect and specific aspects of Customer's legal process
|  | Send client vendor onboarding messaging. Request all freeze period invoices be submitted through new process. | e-Billing | Not Started |  |  | 0%
|  | Customize vendor new submission policy messaging | Customer / e-Billing | Not Started |  |  | 0% |  | We'll customize the messaging to reflect and specific aspects of Customer's legal process
|  | Client to notify vendors of new submission policy | Customer | Not Started |  |  | 0%
|  | Confirm vendors signed up and ready | e-Billing | Not Started |  |  | 0% |  | We'll confirm that vendors have signed up and registered for CounselGO.
T |  | Patent Integration | Not Applicable |  |  |  | 0%
|  | Requirements - mapping of e-Billing fields to custom fields | Customer / e-Billing | Not Started |  |  | 0%
|  | Build integration | Customer / e-Billing | Not Started
|  | Testing with sample data from IP system | Customer / e-Billing | Not Started |  |  | 0%
|  | Production Deployment | Customer / e-Billing | Not Started |  |  | 0%
T |  | Single Sign-On |  |  |  |  | 0%
|  | Single Sign-On Requirements | Customer / e-Billing | Not Started |  |  | 0%
|  | Single Sign-On Setup (Customer) | Customer | Not Started |  |  | 0%
|  | Single Sign-On Setup (e-Billing) | e-Billing | Not Started |  |  | 0%
|  | SSO Testing | Customer / e-Billing | Not Started |  |  | 0%
T |  | Finance Integration |  |  |  |  | 0%
|  | Request flat file structure (e-billing to Finance System inbound, optional acknowledgement, optional but recommended payment confirmation) | Customer | Not Started |  |  | 0%
|  | Review flat file structure and prepare requirements discussion (inbound e-billing to Finance System, optional acknowledgement, optional but recommended payment confirmation) | e-Billing | Not Started |  |  | 0%
|  | Finance Integration Requirements Discussion | Customer / e-Billing | Not Started |  |  | 0%
|  | Build custom flat invoice file or API | e-Billing | Not Started |  |  | 0%
| O | Customer builds response (acknowledgement and or payment confirmation) | Customer | Not Started |  |  | 0%
|  | Send testing plan with multiple scenarios | e-Billing | Not Started |  |  | 0%
|  | Establish secure file transfer or API Webservices connection | Customer / e-Billing | Not Started |  |  | 0%
|  | Conduct finance integration testing | Customer / e-Billing | Not Started |  |  | 0%
|  | Production Deployment into finance system | Customer / e-Billing | Not Started |  |  | 0%
|  | Automate file send and pull | Customer / e-Billing | Not Started |  |  | 0%
T | O | Other Integration or Custom Feature / Report | Not Applicable |  |  |  | 0% |  | Not applicable for most customers
|  | Customer provides requirements to e-Billing (or interface template spec) for e-Billing to review and discuss | Customer / e-Billing | Not Started |  |  | 0%
|  | Design custom feature | e-Billing | Not Started |  |  | 0%
|  | Confirm functionality design with customer | Customer / e-Billing | Not Started |  |  | 0%
|  | Build integration or custom feature | e-Billing | Not Started |  |  | 0%
|  | Testing with sample data from / to e-Billing or test feature | Customer / e-Billing | Not Started |  |  | 0%
|  | Production Deployment | e-Billing | Not Started |  |  | 0%
T |  | Historical data load |  |  |  |  | 0%
|  | Gather Historical data requirements (e.g. system, timeframe, data format) | Customer / e-Billing | Not Started |  |  | 0%
|  | Review sample of historical data | e-Billing | Not Started
|  | Customer provides historical data in agreed upon format | Customer | Not Started
|  | Load historcal data from legacy application | e-Billing | Not Started
|  | Customer to validate historical data load | Customer / e-Billing | Not Started |  |  | 0%
|  | Fix historical data load issues | e-Billing | Not Started |  |  | 0%
T |  | Cutover Process Planning |  |  |  |  | 0%
|  | Draft vendor communication for cutover process | e-Billing | Not Started |  |  | 0%
|  | Send communication to law firms regarding cutover period (if applicable) for when they should start submitting invoices to e-Bililng and stop submitting to old process | Customer / e-Billing | Not Started |  |  | 0%
T |  | Project Communication and User Training |  |  |  |  | 0%
|  | Project communication (could be recurring depending on project team and company size) | Customer / e-Billing | Not Started |  |  | 0%
|  | Schedule training sessions | Customer / e-Billing | Not Started |  |  | 0%
|  | Training communication | Customer / e-Billing | Not Started |  |  | 0%
|  | Prepare Training | e-Billing | Not Started |  |  | 0%
|  | Administrative Roles Training | Customer / e-Billing | Not Started |  |  | 0% |  | An in-depth training for administrative users.
|  | Invoice Reviewers Training | Customer / e-Billing | Not Started |  |  | 0% |  | A training on an invoice lifecycle and reviewing an invoice. This may happen over the course of a few days depending on volume of users.
T |  | Go Live |  |  |  |  | 0%
|  | Receive invoices from Vendors (LEDEs and Digital Files) | e-Billing | Not Started |  |  | 0%
|  | Load new invoices into live system | e-Billing | Not Started |  |  | 0%
|  | UAT - Invoice lifecycle testing | Customer | Not Started |  |  | 0% |  | Test creation of vendor, submission of invoice, review, and payment to identify bugs and final process
|  | Internal launch messaging | Customer | Not Started |  |  | 0%
|  | Go Live Review | Customer | Not Started |  |  | 0% |  | Review data, finance, vendor and account setup
|  | Vendors Submitting to e-Billing | Customer | Not Started |  |  | 0% |  | Invoices begin to flow into e-Billing from law firms
|  | Attorneys reviewing invoice in e-Billing | Customer | Not Started |  |  | 0% |  | Invoices are being reviewed and approved by attorneys
|  | Stabilization review and system tweaks | Customer / e-Billing | Not Started |  |  | 0%
Note on J3: Notes: Blue means there is a template in the process folder to leverage.

## Holidays (hidden)
Holidays to Exclude from Work Days
List special dates that should be considered non-working days.
If your project spans more than one year, add separate dates for each holiday for each year.
Date | Description | Country
2015-12-25 | Christmas
2016-12-25 | Christmas
2017-12-25 | Christmas
2018-12-25 | Christmas
2019-12-25 | Christmas
2020-12-25 | Christmas
2021-12-25 | Christmas
2022-12-25 | Christmas
2023-12-25 | Christmas
2024-12-25 | Christmas
2025-12-25 | Christmas
2015-01-01 | New Year's Day
2016-01-01 | New Year's Day
2017-01-01 | New Year's Day
2018-01-01 | New Year's Day
2019-01-01 | New Year's Day
2020-01-01 | New Year's Day
2021-01-01 | New Year's Day
2022-01-01 | New Year's Day
2023-01-01 | New Year's Day
2024-01-01 | New Year's Day
2025-01-01 | New Year's Day
2015-10-12 | Columbus Day | US
2016-10-10 | Columbus Day | US
2017-10-09 | Columbus Day | US
2018-10-08 | Columbus Day | US
2019-10-14 | Columbus Day | US
2020-10-12 | Columbus Day | US
2021-10-11 | Columbus Day | US
2022-10-10 | Columbus Day | US
2023-10-09 | Columbus Day | US
2024-10-14 | Columbus Day | US
2025-10-13 | Columbus Day | US
2015-07-04 | Independence Day | US
2016-07-04 | Independence Day | US
2017-07-04 | Independence Day | US
2018-07-04 | Independence Day | US
2019-07-04 | Independence Day | US
2020-07-04 | Independence Day | US
2021-07-04 | Independence Day | US
2022-07-04 | Independence Day | US
2023-07-04 | Independence Day | US
2024-07-04 | Independence Day | US
2025-07-04 | Independence Day | US
2015-09-07 | Labor Day | US
2016-09-05 | Labor Day | US
2017-09-04 | Labor Day | US
2018-09-03 | Labor Day | US
2019-09-02 | Labor Day | US
2020-09-07 | Labor Day | US
2021-09-06 | Labor Day | US
2022-09-05 | Labor Day | US
2023-09-04 | Labor Day | US
2024-09-02 | Labor Day | US
2025-09-01 | Labor Day | US
2015-01-19 | M.L.King Jr. Day | US
2016-01-18 | M.L.King Jr. Day | US
2017-01-16 | M.L.King Jr. Day | US
2018-01-15 | M.L.King Jr. Day | US
2019-01-21 | M.L.King Jr. Day | US
2020-01-20 | M.L.King Jr. Day | US
2021-01-18 | M.L.King Jr. Day | US
2022-01-17 | M.L.King Jr. Day | US
2023-01-16 | M.L.King Jr. Day | US
2024-01-15 | M.L.King Jr. Day | US
2025-01-20 | M.L.King Jr. Day | US
2015-05-25 | Memorial Day | US
2016-05-30 | Memorial Day | US
2017-05-29 | Memorial Day | US
2018-05-28 | Memorial Day | US
2019-05-27 | Memorial Day | US
2020-05-25 | Memorial Day | US
2021-05-31 | Memorial Day | US
2022-05-30 | Memorial Day | US
2023-05-29 | Memorial Day | US
2024-05-27 | Memorial Day | US
2025-05-26 | Memorial Day | US
2015-02-16 | Presidents Day | US
2016-02-15 | Presidents Day | US
2017-02-20 | Presidents Day | US
2018-02-19 | Presidents Day | US
2019-02-18 | Presidents Day | US
2020-02-17 | Presidents Day | US
2021-02-15 | Presidents Day | US
2022-02-21 | Presidents Day | US
2023-02-20 | Presidents Day | US
2024-02-19 | Presidents Day | US
2025-02-17 | Presidents Day | US
2015-11-26 | Thanksgiving | US
2016-11-24 | Thanksgiving | US
2017-11-23 | Thanksgiving | US
2018-11-22 | Thanksgiving | US
2019-11-28 | Thanksgiving | US
2020-11-26 | Thanksgiving | US
2021-11-25 | Thanksgiving | US
2022-11-24 | Thanksgiving | US
2023-11-23 | Thanksgiving | US
2024-11-28 | Thanksgiving | US
2025-11-27 | Thanksgiving | US
2015-11-11 | Veterans Day | US
2016-11-11 | Veterans Day | US
2017-11-11 | Veterans Day | US
2018-11-11 | Veterans Day | US
2019-11-11 | Veterans Day | US
2020-11-11 | Veterans Day | US
2021-11-11 | Veterans Day | US
2022-11-11 | Veterans Day | US
2023-11-11 | Veterans Day | US
2024-11-11 | Veterans Day | US
2025-11-11 | Veterans Day | US
2015-12-26 | Boxing Day | UK
2016-12-26 | Boxing Day | UK
2017-12-26 | Boxing Day | UK
2018-12-26 | Boxing Day | UK
2019-12-26 | Boxing Day | UK
2020-12-26 | Boxing Day | UK
2021-12-26 | Boxing Day | UK
2022-12-26 | Boxing Day | UK
2023-12-26 | Boxing Day | UK
2024-12-26 | Boxing Day | UK
2025-12-26 | Boxing Day | UK
2015-04-03 | Good Friday | UK
2016-03-25 | Good Friday | UK
2017-04-14 | Good Friday | UK
2018-03-30 | Good Friday | UK
2019-04-19 | Good Friday | UK
2020-04-10 | Good Friday | UK
2021-04-02 | Good Friday | UK
2022-04-15 | Good Friday | UK
2023-04-07 | Good Friday | UK
2024-03-29 | Good Friday | UK
2025-04-18 | Good Friday | UK
2015-04-06 | Easter Monday | UK
2016-03-28 | Easter Monday | UK
2017-04-17 | Easter Monday | UK
2018-04-02 | Easter Monday | UK
2019-04-22 | Easter Monday | UK
2020-04-13 | Easter Monday | UK
2021-04-05 | Easter Monday | UK
2022-04-18 | Easter Monday | UK
2023-04-10 | Easter Monday | UK
2024-04-01 | Easter Monday | UK
2025-04-21 | Easter Monday | UK
2015-05-04 | Early May Bank Holiday | UK
2016-05-02 | Early May Bank Holiday | UK
2017-05-01 | Early May Bank Holiday | UK
2018-05-07 | Early May Bank Holiday | UK
2019-05-06 | Early May Bank Holiday | UK
2020-05-04 | Early May Bank Holiday | UK
2021-05-03 | Early May Bank Holiday | UK
2022-05-02 | Early May Bank Holiday | UK
2023-05-01 | Early May Bank Holiday | UK
2024-05-06 | Early May Bank Holiday | UK
2025-05-05 | Early May Bank Holiday | UK
2015-05-25 | Spring Bank Holiday | UK
2016-05-30 | Spring Bank Holiday | UK
2017-05-29 | Spring Bank Holiday | UK
2018-05-28 | Spring Bank Holiday | UK
2019-05-27 | Spring Bank Holiday | UK
2020-05-25 | Spring Bank Holiday | UK
2021-05-31 | Spring Bank Holiday | UK
2022-05-30 | Spring Bank Holiday | UK
2023-05-29 | Spring Bank Holiday | UK
2024-05-27 | Spring Bank Holiday | UK
2025-05-26 | Spring Bank Holiday | UK
2015-08-03 | Summer Bank Holiday | UK
2016-08-01 | Summer Bank Holiday | UK
2017-08-07 | Summer Bank Holiday | UK
2018-08-06 | Summer Bank Holiday | UK
2019-08-05 | Summer Bank Holiday | UK
2020-08-03 | Summer Bank Holiday | UK
2021-08-02 | Summer Bank Holiday | UK
2022-08-01 | Summer Bank Holiday | UK
2023-08-07 | Summer Bank Holiday | UK
2024-08-05 | Summer Bank Holiday | UK
2025-08-04 | Summer Bank Holiday | UK
2015-08-31 | Late Summer Bank Holiday | UK
2016-08-29 | Late Summer Bank Holiday | UK
2017-08-28 | Late Summer Bank Holiday | UK
2018-08-27 | Late Summer Bank Holiday | UK
2019-08-26 | Late Summer Bank Holiday | UK
2020-08-31 | Late Summer Bank Holiday | UK
2021-08-30 | Late Summer Bank Holiday | UK
2022-08-29 | Late Summer Bank Holiday | UK
2023-08-28 | Late Summer Bank Holiday | UK
2024-08-26 | Late Summer Bank Holiday | UK
2025-08-25 | Late Summer Bank Holiday | UK